## Sheet1
Task | Start | End | Duration (Days) | Dependency
Problem Statement Documentation | 2025-10-27 | 2025-11-02 | 7 | -
Project Objectives Definition | 2025-11-03 | 2025-11-05 | 2 | Problem Statement
Stakeholder Identification | 2025-11-04 | 2025-11-08 | 4 | Project Objectives
Supervisor Review and Feedback |  |  |  | All previous tasks
Final Document Submission | 10/28/2025 | 11/09/2025 | 2 | Supervisor Review